SERVICE LEVEL AGREEMENT

Azibuye Emasisweni MaQamu Community Trust (IT 1021/2007) and Bathunywe Business Enterprise

| Date | 6 April 2026 |
| --- | --- |
| Reference | BBE/ACT/2026/SLA/001 |
| Client (Trust) | Azibuye Emasisweni MaQamu Community Trust (IT 1021/2007) |
| Agent | Bathunywe Business Enterprise |
| Subject | Strategic Implementing Agent Services — Lion Park Land Formalisation Programme |

1. PARTIES

1.1  The Azibuye Emasisweni MaQamu Community Trust, registered under IT 1021/2007, acting through its duly authorised Board of Trustees ("the Trust" or "the Client").

1.2  Bathunywe Business Enterprise, a South African business entity, represented by Ms Thembeka P Ndlovu-Nkabinde as Managing Director ("Bathunywe" or "the Agent").

1.3  The parties are collectively referred to as the "Parties" and individually as a "Party".

2. APPOINTMENT AND SCOPE

2.1  The Trust appoints Bathunywe as its exclusive Strategic Implementing Agent for the Lion Park Land Formalisation Programme ("the Programme") with effect from 6 April 2026, for the initial period set out in clause 3.

2.2  The scope of services includes: funding mobilisation; stakeholder coordination; occupier registration and Occupancy Certificate programme; community engagement and social facilitation; township establishment technical oversight; Programme Revenue Account administration; and all programme management functions as detailed in the Formal Proposal dated April 2026 (incorporated by reference).

2.3  Kwahlelwa Group (Ms Lonathemba Radebe) is acknowledged as the Technology Partner responsible for the LandLink digital platform. The terms of Kwahlelwa Group's engagement are governed by a separate Technology Partnership Agreement between Bathunywe and Kwahlelwa Group, which shall impose no direct financial obligations on the Trust beyond those in this Agreement.

3. DURATION

3.1  This Agreement commences on 6 April 2026 and continues for an initial term of 36 (thirty-six) months.

3.2  The Agreement renews automatically for 12-month periods unless either Party gives 60 days' written notice of non-renewal prior to the expiry of any term.

4. BATHUNYWE'S OBLIGATIONS

- Deploy a dedicated programme team within 5 business days of 6 April 2026;

- Commence the Occupier Census within 30 days of LandLink platform readiness;

- Submit a minimum of two funding applications on behalf of the Trust within 60 days;

- Deliver a written monthly progress and financial report to the Trust by the 7th of each calendar month;

- Maintain professional indemnity insurance appropriate to the mandate scope;

- Comply with all applicable legislation including the Trust Property Control Act 57 of 1988, POPIA, the Restitution of Land Rights Act 22 of 1994 as amended, and all relevant human settlements legislation;

- Maintain open-book programme financial records, available to the Trustees on 5 business days' written notice.

5. TRUST'S OBLIGATIONS

- Provide Bathunywe with all programme-relevant documentation including the Trust Deed, title deed information, RLCC correspondence, and court order documentation;

- Attend monthly review meetings (in person or by videoconference) with Bathunywe;

- Issue all required resolutions, authorisations, and letters within 5 business days of written request;

- Not appoint any other party to perform services within the scope of this Agreement without Bathunywe's prior written consent.

6. PROGRAMME REVENUE ACCOUNT

6.1  A dedicated Programme Revenue Account shall be established at ABSA Bank Limited, in the Trust's name, with Bathunywe as the authorised operating agent.

6.2  All Occupancy Certificate levy collections, registration fees, and programme grants shall be deposited into this account.

6.3  Disbursements shall follow this waterfall order:

- First: ABSA bridging facility repayments (where applicable);

- Second: Bathunywe levy administration fee (8% of gross levies), auto-swept monthly;

- Third: Approved programme operational expenditure;

- Fourth: Trust operating reserve contribution (minimum 10% of monthly balance);

- Fifth: Surplus to Trust development fund.

6.4  Bathunywe shall provide the Trust with a reconciled monthly account statement within 7 days of month-end.

7. INTELLECTUAL PROPERTY

7.1  All programme-specific deliverables (reports, plans, frameworks) produced by Bathunywe vest in the Trust on full payment of the relevant invoices.

7.2  The LandLink platform and all associated technology remain the intellectual property of Kwahlelwa Group. The Trust receives a non-exclusive, non-transferable licence for the duration of this Agreement.

8. REMUNERATION

Remuneration is as set out in Annexure A (Remuneration Schedule) which forms an integral part of this Agreement.

9. TERMINATION

9.1  Either Party may terminate on 60 days' written notice.

9.2  The Trust may terminate immediately on Bathunywe's material breach unremedied within 20 business days of written notice.

9.3  Bathunywe may terminate immediately if any undisputed invoice remains unpaid for more than 30 days beyond its due date.

9.4  On termination, Bathunywe shall deliver all programme records, data, and platform credentials to the Trust within 10 business days, and shall be entitled to all fees earned to the termination date.

10. DISPUTE RESOLUTION

Any dispute shall first be referred to good-faith mediation. If unresolved within 30 days, it shall proceed to arbitration under AFSA rules, seated at Durban, KwaZulu-Natal.

11. GENERAL

11.1  This Agreement constitutes the entire agreement between the Parties and supersedes all prior understandings.

11.2  Amendments require written agreement signed by both Parties.

11.3  This Agreement is governed by the laws of the Republic of South Africa.

| Mr Ngcobo Authorised Trustee For and on behalf of Azibuye Emasisweni MaQamu Community Trust Date: ___________________ |  | Ms Thembeka P Ndlovu-Nkabinde Managing Director Bathunywe Business Enterprise Date: ___________________ |
| --- | --- | --- |

| Witness 1 — Full Name & Signature |  | Witness 2 — Full Name & Signature |
| --- | --- | --- |

ANNEXURE A — REMUNERATION SCHEDULE

To the Service Level Agreement: Azibuye Emasisweni MaQamu Community Trust & Bathunywe Business Enterprise — 6 April 2026

The following remuneration structure is hereby agreed and approved. All amounts exclude VAT. Bathunywe shall issue valid tax invoices for all amounts earned. The Trust's independent auditor may inspect all supporting records on reasonable written notice.

| # | Component | Basis & Trigger | Rate / Amount | Funding Source |
| --- | --- | --- | --- | --- |
| 1 | Monthly Management Retainer Baseline operational presence, reporting, stakeholder coordination. Reduces to R20,000/mo once monthly levy collections exceed R150,000. | Monthly on the 1st. Funded from mobilisation capital during establishment phase. | R 35,000 / month | ABSA Bridging / Section 42C Grant |
| 2 | Registration Fee Share 20% of each R1,500 once-off registration fee per occupier household. Rewards speed and quality of census mobilisation. | Per household, at point of registration fee receipt into Programme Revenue Account. | R 300 per HH est. R240,000 at 800 HH | Occupier registration fees |
| 3 | Levy Administration Fee 8% of gross monthly levy collections. Covers billing, collections, arrears management, and reconciliation. Scales with programme growth. | Auto-swept from Programme Revenue Account on the 3rd business day of each month. | 8% of levies collected est. R14,500/mo now; R40,000/mo at full scale | Programme Revenue Account levy collections |
| 4 | Funding Mobilisation Success Fee 3.5% of all grant funding, DFI loans, or private investment successfully mobilised and received. Fully contingent — earned only on actual drawdown. | On drawdown of each tranche. Bathunywe invoices within 5 business days. Must be disclosed in all funding applications. | 3.5% on drawdown est. R1.05M on R30M HSDG grant | From each funding tranche received |
| 5 | Township Establishment Technical Fees Planning, surveying, EIA coordination, and township registration. Phase-completion invoicing at SACPLAN/SACPVP professional fee guidelines. | Per phase, on written phase-gate sign-off by Trust. Separate quotation approved in advance for each phase. | SACPLAN rates per phase — quoted in advance | Capital programme (DBSA / HSDG infrastructure allocation) |

Payment terms: 30 days from date of valid tax invoice, save where specified otherwise. Late payments attract interest at prime overdraft rate plus 2% per annum, calculated daily from the due date.

The Trust's independent auditor has the right to inspect all records relevant to the computation of levy administration fees and funding success fees, on 5 business days' written notice.

ANNEXURE A SIGNED BY THE PARTIES ON 6 APRIL 2026

| Mr Ngcobo Azibuye Emasisweni MaQamu Community Trust Authorised Trustee Date: ___________________ |  | Ms T P Ndlovu-Nkabinde Bathunywe Business Enterprise Managing Director Date: ___________________ |
| --- | --- | --- |